## Task Master
Organization Name | Industry | Parent Task ID | Task ID | Working Day | Fiscal Period | Period Type | Organization Level | Lowest Org Level Name | Area | Region | Country | Entity | Owner Function | Task Owner | Backup Task Owner | Phase | Task Description | Input Source | Output Artifact | Dependency Task | Dependency Type | Priority | SLA Hours | Human Approval Required | Approval Role | AI Enabled | AI Action | AI Confidence Threshold | Variance Threshold Rule ID | Variance Threshold Rule | Functional Currency | Reporting Currency | Escalation Rule ID | Escalation Rule | Exception Logic | Status | Completon % | Escalation Role | Escalation After Hours | Escalated | Comments | Audit Timestamp | Audit Stamp | AI Action - Planned Wave 2
Helvetia Advisory AG | Technology | PC000 | PC001 | WD-5 | 2026 P05 | Monthly | Global | Global | NA | NA | NA | NA | FP&A | Central FP&A Lead | Central FP&A Analyst | Pre-Close | Publish close calendar | Excel | Close Calendar PDF | None | Finish To Start | High | 4 | Yes | FP&A Director | No | NA | NA | NA | NA | CHF | CHF | ER001 | Escalate if not published by WD-5 09:00 | Not published within 2 hours of WD-5 start | Complete | 100 | FP&A Director | 2 | No | Close calendar published on schedule |  |  | Generate dynamic close schedule, predict bottlenecks based on prior period delays
Helvetia Advisory AG | Technology | PC000 | PC002 | WD-5 | 2026 P05 | Monthly | Global | Global | NA | NA | NA | NA | Group Controller | Global Controlling Lead | Global Controlling Deputy Lead | Pre-Close | Publish accounting cutoffs | Excel | Cutoff Rules Document | None | Finish To Start | High | 4 | Yes | Group Controller | No | NA | NA | NA | NA | CHF | CHF | ER001 | Escalate if not published by WD-5 12:00 | Not published within 4 hours of WD-5 start | Complete | 100 | Group Controller | 4 | No | Accounting cutoffs confirmed and distributed |  |  | NA
Helvetia Advisory AG | Technology | PC000 | PC003 | WD-5 | 2026 P05 | Monthly | Global | Global | NA | NA | NA | NA | FP&A | Central FP&A Lead | Central FP&A Analyst | Pre-Close | Issue submission templates | Excel | Submission Template Pack | PC001 and PC002 | Finish To Start | High | 3 | Yes | Central FP&A Lead | No | NA | NA | NA | NA | CHF | CHF | ER001 | Escalate if templates not issued by WD-5 EOD | Templates not issued within SLA | Complete | 100 | FP&A Director | 3 | No | Submission templates issued to all business owners |  |  | Auto-populate templates from prior period, flag structural changes
Helvetia Advisory AG | Technology | PC000 | PC004 | WD-4 | 2026 P05 | Monthly | Global | Global | NA | NA | NA | NA | IT | Global IT Manager | Global IT Deputy Manager | Pre-Close | Validate interfaces and refresh jobs | ERP | Interface Health Report | PC002 | Parallel | High | 4 | Yes | Global IT Manager | No | NA | NA | NA | NA | CHF | CHF | ER003 | Retry failed interfaces, escalate to IT lead after 2 retries | Interface failure or data refresh gap detected | Complete | 100 | Global IT Manager | 2 | No | All interfaces validated, no refresh failures detected |  |  | Monitor interface health, auto-retry failed jobs, alert on data gaps
Helvetia Advisory AG | Technology | PC000 | PC005 | WD-4 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Pre-Close | Notify business owners | Excel | Notification Log | PC003 | Finish To Start | Medium | 2 | No | NA | No | NA | NA | NA | NA | CHF | CHF | ER001 | Escalate if notifications not confirmed sent by WD-4 12:00 | Notification delivery failure | Complete | 100 | Regional FP&A Lead | 2 | No | Business owner notifications sent and confirmed |  |  | Generate and send automated notifications to business owners
Helvetia Advisory AG | Technology | PC000 | PC006 | WD-4 | 2026 P05 | Monthly | Global | Global | NA | NA | NA | NA | IT | Central Data Lead | Central Data Analyst | Pre-Close | Validate hierarchy changes | ERP | Hierarchy Validation Sign-off | PC001 and PC002 | Finish To Start | High | 3 | Yes | Central Data Lead | No | NA | NA | NA | NA | CHF | CHF | ER005 | Suggest mapping fix, escalate to master data owner | Hierarchy mismatch detected in ERP | Complete | 100 | Central Data Lead | 2 | No | Hierarchy validated, no mapping mismatches found |  |  | Validate hierarchy mappings, flag mismatches against prior period
Helvetia Advisory AG | Technology | PC000 | PC007 | WD-4 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | HR | Regional HR Lead | Regional HR Deputy Lead | Pre-Close | Validate headcount movement | HR System | Headcount Validation Report | PC005 and PC006 | Parallel | High | 4 | Yes | Regional HR Lead | Yes | Detect headcount anomalies vs plan, flag unexpected hires or exits | 80 | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER001 | Escalate if headcount delta exceeds threshold without explanation | Headcount movement outside approved plan | Complete | 100 | Regional HR Lead | 3 | No | Headcount movement validated - 3 exceptions flagged and under review by HR |  |  | NA
Helvetia Advisory AG | Technology | PC000 | PC008 | WD-4 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Procurement | Regional Procurement Lead | Regional Procurement Deputy Lead | Pre-Close | Open PO review | PO System | PO Commitment Report | PC005 and PC006 | Parallel | Medium | 4 | Yes | Regional Procurement Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER001 | Escalate if open POs exceed materiality threshold unreviewed | PO aging or commitment spike vs prior period | Complete | 100 | Regional Procurement Lead | 4 | No | Open PO review complete, 2 aging commitments flagged |  |  | Flag aging POs over 90 days, identify uncommitted spend at risk
Helvetia Advisory AG | Technology | PC000 | PC009 | WD-4 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Sales Ops | Regional Sales Ops Lead | Regional Sales Ops Deputy Lead | Pre-Close | Revenue pipeline validation | ERP | Pipeline Validation Report | PC005 and PC006 | Parallel | High | 4 | Yes | Regional Sales Ops Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER004 | Create investigation task if pipeline variance unexplained | Revenue pipeline variance vs forecast exceeds 5% | Complete | 100 | Regional Controlling Lead | 3 | No | Revenue pipeline validated, minor variance within threshold |  |  | Compare pipeline to prior period, flag revenue assumption anomalies
Helvetia Advisory AG | Technology | PC000 | PC010 | WD-3 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Controller | Regional Controlling Lead | Regional Controlling Deputy Lead | Pre-Close | Review expected accruals | ERP | Accrual Estimate List | PC006, PC007, PC008 and PC009 | Finish To Start | High | 6 | Yes | Regional Controlling Lead | Yes | Suggest accruals based on historical patterns, flag missing or anomalous entries | 85 | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER002 | Estimate accrual using historical pattern, escalate to Controller | Expected accrual missing or materially different from prior period | Complete | 100 | Regional Controlling Lead | 2 | No | Expected accruals reviewed and approved |  |  | NA
Helvetia Advisory AG | Technology | PC000 | PC011 | WD-3 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Pre-Close | Review forecast assumptions | Excel | Forecast Assumption Log | PC009 and PC010 | Finish To Start | High | 4 | Yes | Regional FP&A Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER001 | Escalate if assumptions not reviewed by WD-3 EOD | Forecast assumption change exceeds 5% without commentary | Complete | 100 | Regional FP&A Lead | 4 | No | Forecast assumptions reviewed and signed off |  |  | Variance prediction against prior forecast, flag assumption drift
Helvetia Advisory AG | Technology | CL000 | CL000-1 | WD-1 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Operations | Operations Specialist | Operations Junior Specialist | Close | Reconcile for end of day sales and returns | ERP | Sales Reconciliation Report | Pre-Close Tasks | Finish To Start | High | 4 | No | NA | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER001 | Escalate if unreconciled balance remains at WD-1 EOD | Unreconciled sales balance above CHF 10K at close | Complete | 100 | Operations Specialist | 2 | No | End of day sales and returns reconciled successfully |  |  | Monitor sales reconciliation completeness, flag unreconciled items
Helvetia Advisory AG | Technology | CL000 | CL000-2 | WD-1 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Accounts Receivable | Invoicing Specialist | Invoicing Junior Specialist | Close | Complete invoicing | ERP | Invoice Completion Confirmation | Pre-Close Tasks | Finish To Start | High | 3 | No | NA | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER001 | Escalate if invoicing not complete by WD-1 18:00 | Open invoices remaining after cutoff | Complete | 100 | Invoicing Specialist | 2 | No | Invoicing completed before cutoff |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL000-3 | WD-1 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Accounts Receivable | Accounts Receivable Specialist | Accounts Receivable Junior Specialist | Close | Review, reconcile and post for unapplied receipts, deposits, payments, bad debts and chargeback invoices | ERP | AR Reconciliation Report | Pre-Close Tasks | Finish To Start | High | 5 | Yes | Accounts Receivable Specialist | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER001 | Escalate if unapplied balance exceeds CHF 50K at WD-1 EOD | Unapplied receipts or bad debt spike vs prior period | Blocked | 0 | Regional Controlling Lead | 2 | Yes | AR reconciliation blocked - CHF 87K unapplied receipts unresolved, escalated to Regional Controlling Lead |  |  | Flag unapplied receipts above threshold, suggest posting treatment
Helvetia Advisory AG | Technology | CL000 | CL000-4 | WD-1 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Payroll | Payroll Specialist | Payroll Junior Specialist | Close | Accrue for leaves, benefits, bonus, and time worked not paid till next month | ERP | Payroll Accrual Journal | Pre-Close Tasks | Finish To Start | High | 4 | Yes | Payroll Specialist | Yes | Detect headcount exception in accrual vs validated headcount report | 85 | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER002 | Estimate accrual using historical pattern if submission missing | Payroll accrual variance vs prior period exceeds 5% | Complete | 100 | Regional HR Lead | 2 | No | Payroll accruals posted, headcount exception noted and flagged |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL000-5 | WD-1 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Payroll | Payroll Specialist | Payroll Junior Specialist | Close | Reconcile for employee receivables and tax liabilities | ERP | Payroll Reconciliation Report | Pre-Close Tasks | Finish To Start | Medium | 3 | Yes | Payroll Specialist | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER001 | Escalate if reconciliation not complete by WD-1 EOD | Unreconciled employee receivable or tax liability | Complete | 100 | Regional Controlling Lead | 3 | No | Employee receivables and tax liabilities reconciled |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL000-6 | WD-1 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Accounts Payable | Accounts Payable Specialist | Accounts Payable Junior Specialist | Close | Identify and update unbooked invoices and post for all payable transactions | ERP | AP Posting Confirmation | Pre-Close Tasks | Finish To Start | High | 4 | Yes | Accounts Payable Specialist | Yes | Flag unbooked invoices above threshold, identify missing accruals | 80 | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER002 | Estimate accrual for late invoices using historical pattern | Unbooked invoice above CHF 25K detected at cutoff | Blocked | 0 | Regional Controlling Lead | 2 | Yes | AP posting blocked - 2 unbooked invoices totalling CHF 43K pending supplier confirmation |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL000-7 | WD-1 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Treasury | Treasury Specialist | Treasury Junior Specialist | Close | Reconcile bank statements, petty cash, inter-co borrowings/cash transactions, equity/loan accounts and book finance/interest charges | ERP | Treasury Reconciliation Report | Pre-Close Tasks | Finish To Start | High | 5 | Yes | Treasury Specialist | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER001 | Escalate if bank break exceeds CHF 10K unresolved | Bank reconciliation break or inter-co mismatch | Complete | 100 | Treasury Specialist | 2 | No | Bank and inter-co accounts reconciled, no breaks identified |  |  | Flag bank reconciliation breaks, detect unusual inter-co balances
Helvetia Advisory AG | Technology | CL000 | CL001-1 | WD-1 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Verify prior month's reversal entries | ERP | Reversal Verification Log | Pre-Close Tasks | Finish To Start | Medium | 2 | No | NA | No | NA | NA | NA | NA | CHF | CHF | ER001 | Escalate if reversal missing at WD-1 start | Prior month reversal entry absent from journal | Complete | 100 | Regional Snr. Accountant | 1 | No | Prior month reversal entries verified and confirmed |  |  | Verify prior period reversals posted correctly, flag missing reversals
Helvetia Advisory AG | Technology | CL000 | CL001-2 | WD-1 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Contact other departments (AR, AP, Inventory, Payroll) for transaction status | Email/Manual | Department Status Log | Pre-Close Tasks | Finish To Start | Medium | 2 | No | NA | No | NA | NA | NA | NA | CHF | CHF | ER001 | Escalate if no response received within 2 hours | No response from department within SLA | Complete | 100 | Regional Snr. Accountant | 2 | No | Department status confirmed - AR and AP flagged as in progress at time of contact |  |  | Send automated status requests to AR, AP, Inventory, Payroll teams
Helvetia Advisory AG | Technology | CL000 | CL001-3 | WD-1 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Review and process deferred expenses | ERP | Deferred Expense Journal | Pre-Close Tasks | Finish To Start | Medium | 3 | Yes | Regional Snr. Accountant | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER001 | Escalate if deferred expense balance materially different from prior period | Deferred expense movement outside expected range | Complete | 100 | Regional Controlling Lead | 3 | No | Deferred expenses reviewed and journals posted |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL001-4 | WD-1 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Review prepaid expenses and post journal entries | ERP | Prepaid Expense Journal | Pre-Close Tasks | Finish To Start | Medium | 3 | Yes | Regional Snr. Accountant | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER001 | Escalate if prepaid balance spike detected | Prepaid expense movement outside expected range | Complete | 100 | Regional Controlling Lead | 3 | No | Prepaid expenses reviewed and journals posted |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL001-5 | WD-1 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Review accruals and post journal entries | ERP | Accrual Journal Pack | Pre-Close Tasks | Finish To Start | High | 4 | Yes | Regional Snr. Accountant | Yes | Suggest missing accruals based on historical posting patterns | 85 | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER002 | Estimate accrual using prior period if submission missing | Accrual missing or materially below prior period without explanation | Complete | 100 | Regional Controlling Lead | 2 | No | Accruals reviewed - suggested accruals AI feature flagged 1 missing accrual for software licence renewal CHF 28K, posted after controller review |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL001-6 | WD-1 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Reconcile suspense accounts | ERP | Suspense Account Clearance Report | Pre-Close Tasks | Finish To Start | High | 3 | Yes | Regional Snr. Accountant | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER001 | Escalate if suspense balance above CHF 5K uncleared at EOD | Suspense account balance remaining at period close | Complete | 100 | Regional Controlling Lead | 2 | No | Suspense accounts cleared, no remaining balances |  |  | Flag uncleared suspense balances, suggest clearing entries
Helvetia Advisory AG | Technology | CL000 | CL001-7 | WD-1 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Tax | Regional Tax Lead | Regional Tax Analyst | Close | Calculate and post monthly tax provision entry including current and deferred tax | ERP | Tax Provision Journal | Pre-Close Tasks | Finish To Start | High | 3 | Yes | Regional Tax Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER001 | Escalate if tax provision not posted by WD-1 EOD | Tax provision materially different from prior period without explanation | Complete | 100 | Regional Tax Lead | 2 | No | Tax provision calculated and posted - current tax CHF 312K, deferred tax movement CHF 18K |  |  | Flag tax provision anomalies vs effective tax rate trend
Helvetia Advisory AG | Technology | CL000 | CL001-8 | WD-1 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Run and review monthly depreciation and amortisation journals for all fixed and intangible assets | ERP | Depreciation Journal Confirmation | Pre-Close Tasks | Finish To Start | Medium | 3 | Yes | Regional Snr. Accountant | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER001 | Escalate if depreciation run not confirmed by WD-1 EOD | Depreciation charge materially different from prior period without explanation | Complete | 100 | Regional Controlling Lead | 3 | No | Depreciation and amortisation journals run and reviewed - total charge CHF 89K in line with asset register |  |  | Flag depreciation charge anomalies vs asset register movements
Helvetia Advisory AG | Technology | CL000 | CL001-9 | WD-1 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Treasury | Treasury Specialist | Treasury Junior Specialist | Close | Run monthly FX revaluation for all foreign currency balance sheet positions and book revaluation journals | ERP | FX Revaluation Journal | CL000-3, CL000-6 and CL000-7 | Finish To Start | High | 3 | Yes | Treasury Specialist | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER001 | Escalate if FX revaluation not posted by WD-1 EOD | FX revaluation gain or loss materially different from prior period without explanation | Complete | 100 | Treasury Specialist | 2 | No | FX revaluation completed - net revaluation loss CHF 24K on USD and EUR-denominated receivables |  |  | FX anomaly checks vs market rates, flag unusual revaluation movements
Helvetia Advisory AG | Technology | CL000 | CL002 | WD-1 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Review and reconcile clearing accounts | ERP | Clearing Account Report | CL001 | Finish To Start | High | 3 | Yes | Regional Snr. Accountant | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER001 | Escalate if clearing account aged items exceed CHF 10K | Clearing account item aged over 30 days | Complete | 100 | Regional Controlling Lead | 2 | No | Clearing accounts reconciled, no aged items above threshold |  |  | Check clearing account completeness, flag aged items
Helvetia Advisory AG | Technology | CL000 | CL003-1 | WD-1 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Reconcile and close subledger | ERP | Subledger Close Confirmation | CL002 | Finish To Start | High | 4 | Yes | Regional Controlling Lead | Yes | Missing account checks - validate all accounts posted vs expected | 90 | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER001 | Escalate immediately if subledger close fails | Any account in expected posting list with zero balance | Complete | 100 | Regional Controlling Lead | 1 | No | Subledger closed successfully - missing account check identified 2 accounts with unexpected zero balances, investigated and resolved |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL003-2 | WD-1 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | Controller | Regional Controlling Lead | Regional Controlling Deputy Lead | Close | Reconcile intercompany balances and confirm matched pairs with counterpart entities before period lock | ERP | Intercompany Reconciliation Confirmation | CL002 | Finish To Start | High | 4 | Yes | Regional Controlling Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER001 | Escalate if intercompany reconciliation not confirmed by WD-1 EOD | Intercompany mismatch above CHF 10K unresolved at period lock | In Progress | 50 | Regional Controlling Lead | 2 | No | Intercompany balances reconciled with Austria confirmed. Switzerland-Germany inter-co mismatch of EUR 62K outstanding - under investigation with BU002 treasury team. |  |  | Detect intercompany mismatch patterns, suggest offset entries
Helvetia Advisory AG | Technology | CL000 | CL004 | WD+0 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Close | Generate P&L | ERP | P&L Report | CL003-1 and CL003-2 | Finish To Start | High | 2 | Yes | Regional FP&A Lead | Yes | Missing account checks on P&L, flag zero-balance accounts expected to post | 90 | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER004 | Create investigation task for unexplained P&L movement | P&L line materially different from prior period without explanation | Complete | 100 | Regional FP&A Lead | 1 | No | P&L generated - revenue CHF 4.2M, 3% above forecast |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL005 | WD+0 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Close | Generate flash reports | ERP | Flash Report Pack | CL003-1, CL003-2 and CL004 | Parallel | High | 2 | Yes | Regional FP&A Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER001 | Escalate if flash report not generated by WD+0 12:00 | Flash report generation failure or missing data feed | Complete | 100 | Regional FP&A Lead | 2 | No | Flash reports generated and distributed to leadership |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL006 | WD+0 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Close | Generate forecast update | ERP | Updated Forecast File | CL003-1, CL003-2 and CL004 | Parallel | High | 3 | Yes | Regional FP&A Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | CHF | CHF | ER001 | Escalate if forecast update not complete by WD+0 EOD | Forecast file missing or not refreshed with actuals | Complete | 100 | Regional FP&A Lead | 2 | No | Forecast update complete - actuals loaded and assumption reviewed/updated |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL007 | WD+0 | 2026 P05 | Monthly | BU | BU001 | EMEA | DACH | Switzerland | BU001 | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Close | Draft commentary | Excel | Draft Commentary Document | CL003-1, CL003-2 and CL004 | Parallel | High | 4 | Yes | Regional FP&A Lead | Yes | CFO status email draft based on current close progress | 75 | NA | NA | CHF | CHF | ER001 | Escalate if commentary not drafted by WD+0 EOD | Commentary missing or inconsistent with P&L output | In Progress | 50 | Regional FP&A Lead | 4 | No | Commentary draft in progress - narrative consistency check flagged 2 lines where commentary understates variance magnitude |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL008-REG | WD+1 | 2026 P05 | Monthly | Region | DACH | EMEA | DACH | NA | NA | FP&A | DACH FP&A Lead | DACH Finance Manager | Close-to-Post-Close | Consolidate DACH BU submissions from Switzerland, Germany and Austria and validate completeness before EMEA aggregation | ERP | DACH Consolidated Pack | CL005, CL006 and CL007 for all three BUs | Finish To Start | High | 5 | Yes | DACH Finance Manager | No | NA | NA | VR002 | Region variance >4% or >CHF 500K triggers review | CHF | CHF | ER001 | Escalate if any BU submission missing at WD+1 09:00 | BU submission absent or Germany close not complete by WD+1 09:00 | In Progress | 30 | DACH Finance Manager | 2 | No | DACH consolidation in progress - Austria submitted cleanly, Switzerland submitted with 2 blocked items under resolution, Germany submission delayed due to AR and AP blockages - escalation risk if Germany does not close by WD+1 12:00 |  |  | Cross-BU variance pattern detection, flag structural differences between entities
Helvetia Advisory AG | Technology | CL000 | CL008-CPC | WD+1 | 2026 P05 | Monthly | Region | DACH | EMEA | DACH | NA | NA | FP&A | Regional FP&A Lead | Regional Finance Manager | Close-to-Post-Close | Consolidate region submissions and validate completeness before post-close analysi | ERP | Region Consolidated Pack | CL008-REG | Finish To Start | High | 4 | Yes | Regional Finance Manager | No | NA | NA | VR002 | Region variance >4% or >CHF 500K triggers review | CHF | CHF | ER001 | Escalate if any Region submissions missing at WD+1 09:00 | Region submission absent or materially incomplete | In Progress | 50 | Regional Finance Manager | 2 | No | EMEA consolidation awaiting DACH consolidated pack - Germany delay creating risk to WD+1 timeline |  |  | Validate consolidation completeness, flag missing BU submissions
Helvetia Advisory AG | Technology | CL000 | CL009 | WD+1 | 2026 P05 | Monthly | Region | DACH | EMEA | DACH | NA | NA | Controller | Regional Controlling Lead | Regional Controlling Deputy Lead | Post-Close | Validate accounting completeness | ERP | Completeness Sign-off | CL008-CPC | Finish To Start | High | 3 | Yes | Regional Controlling Lead | Yes | Missing account checks at regional level, cross-BU consistency check | 90 | VR002 | Region variance >4% or >CHF 500K triggers review | CHF | CHF | ER001 | Escalate if completeness gaps found unresolved within 2 hours | Account missing at region level present at BU level | In Progress | 50 | Regional Controlling Lead | 2 | No | Accounting completeness validation in progress - missing account check running across regional submissions |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL010 | WD+1 | 2026 P05 | Monthly | Region | DACH | EMEA | DACH | NA | NA | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Post-Close | Variance analysis | ERP | Variance Analysis Report | CL008-CPC and CL009 | Finish To Start | High | 5 | Yes | Regional FP&A Lead | Yes | Variance root cause suggestions - flag drivers, suggest explanations | 80 | VR002 | Region variance >4% or >CHF 500K triggers review | CHF | CHF | ER004 | Create investigation task for any variance above threshold | Variance above threshold without root cause assigned | In Progress | 50 | Regional FP&A Lead | 2 | No | Variance analysis in progress - AI root cause feature flagged headcount cost overage CHF 156K driven by 4 unplanned contractor engagements in Q2 |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL011 | WD+1 | 2026 P05 | Monthly | Region | DACH | EMEA | DACH | NA | NA | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Post-Close | KPI generation | ERP | KPI Dashboard | CL010 | Finish To Start | Medium | 3 | No | NA | No | NA | NA | VR002 | Region variance >4% or >CHF 500K triggers review | CHF | CHF | ER001 | Escalate if KPI dashboard not generated by WD+1 EOD | KPI data feed failure or missing metric | Not Started | 0 | Regional FP&A Lead | 3 | No | Awaiting variance analysis completion |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL012 | WD+1 | 2026 P05 | Monthly | Region | DACH | EMEA | DACH | NA | NA | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Post-Close | Executive summary draft | Variance Analysis Output / KPI Report | Executive Summary Document | CL010 and CL011 | Finish To Start | High | 4 | Yes | Regional FP&A Lead | Yes | Narrative consistency check - validate commentary aligns with variance data | 80 | VR002 | Region variance >4% or >CHF 500K triggers review | CHF | CHF | ER001 | Escalate if executive summary not submitted by WD+1 EOD | Commentary inconsistent with reported numbers | Not Started | 0 | Regional Finance Manager | 3 | No | Awaiting KPI generation and variance analysis sign-off |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL013 | WD+2 | 2026 P05 | Monthly | Area | EMEA | EMEA | NA | NA | NA | FP&A | Area FP&A Lead | Area Finance Manager | Post-Close | Aggregate regions | ERP | Regional Consolidated Pack | CL012 | Finish To Start | High | 4 | Yes | Area FP&A Lead | No | NA | NA | VR003 | Area variance >3% or >CHF 1M triggers review | CHF | CHF | ER001 | Escalate if any region missing at WD+2 09:00 | Regional submission absent or structurally inconsistent | Not Started | 0 | Area FP&A Lead | 2 | No | Awaiting regional submission consolidation |  |  | Aggregate and validate regional submissions, flag outliers
Helvetia Advisory AG | Technology | CL000 | CL014 | WD+2 | 2026 P05 | Monthly | Area | EMEA | EMEA | NA | NA | NA | Controller | Area Controlling Lead | Area Deputy Controlling Lead | Post-Close | Validate consolidation | ERP | Consolidation Validation Report | CL013 | Finish To Start | High | 3 | Yes | Area Controlling Lead | No | NA | NA | VR003 | Area variance >3% or >CHF 1M triggers review | CHF | CHF | ER006 | Impact analysis if prior period restatement detected | Consolidation eliminations mismatch or inter-area balance break | Not Started | 0 | Area Controlling Lead | 2 | No | Awaiting regional aggregation |  |  | Cross-regional consistency checks, inter-area elimination validation
Helvetia Advisory AG | Technology | CL000 | CL015 | WD+2 | 2026 P05 | Monthly | Area | EMEA | EMEA | NA | NA | NA | Area Leadership | Area Business Lead | Area Business Deputy Lead | Post-Close | Materiality review | Management Pack / Executive Summary | Materiality Review Sign-off | CL013 and CL014 | Finish To Start | High | 3 | Yes | Area Business Lead | Yes | Narrative consistency check on area management pack | 80 | VR003 | Area variance >3% or >CHF 1M triggers review | CHF | CHF | ER004 | Create investigation task if material item lacks commentary | Material variance without written explanation in pack | Not Started | 0 | Area Business Lead | 3 | No | Awaiting consolidation validation |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL016 | WD+3 | 2026 P05 | Monthly | Global | Global | NA | NA | NA | NA | FP&A | Central FP&A Lead | Central FP&A Analyst | Post-Close | Global consolidation | ERP | Global Consolidated Pack | CL015 | Finish To Start | High | 4 | Yes | Central FP&A Lead | Yes | Global consolidation completeness check, missing account checks at global level | 90 | VR004 | Global variance >3% or >CHF 1.5M triggers review | CHF | CHF | ER001 | Escalate if any area submission missing at WD+3 09:00 | Area submission absent or global elimination mismatch | Not Started | 0 | Central FP&A Lead | 1 | No | Awaiting area materiality review |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL017 | WD+3 | 2026 P05 | Monthly | Global | Global | NA | NA | NA | NA | Group Controller | Group Controller | Group Deputy Controller | Post-Close | Final accounting review | ERP | Final Accounting Sign-off | CL016 | Finish To Start | High | 3 | Yes | Group Controller | Yes | Final variance root cause summary, flag unresolved items for sign-off | 85 | VR004 | Global variance >3% or >CHF 1.5M triggers review | CHF | CHF | ER006 | Impact analysis if restatement risk identified | Unresolved variance or open investigation task at sign-off stage | Not Started | 0 | Group Controller | 1 | No | Awaiting global consolidation |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL018 | WD+3 | 2026 P05 | Monthly | Global | Global | NA | NA | NA | NA | Finance Leadership | Global Finance Lead | Global Deputy Finance Lead | Post-Close | Executive sign off | Management Pack / Executive Summary | Signed Management Pack | CL017 | Finish To Start | High | 2 | Yes | Global Finance Lead | No | NA | NA | VR004 | Global variance >3% or >CHF 1.5M triggers review | CHF | CHF | ER001 | Escalate immediately if sign-off not received by WD+3 15:00 | Sign-off not received within SLA | Not Started | 0 | Global Finance Lead | 1 | No | Awaiting final accounting review |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL019 | WD+3 | 2026 P05 | Monthly | Global | Global | NA | NA | NA | NA | FP&A | Central FP&A Lead | Central FP&A Analyst | Post-Close | Final publication | ERP | Published Management Pack | CL018 | Finish To Start | High | 2 | Yes | Central FP&A Lead | No | NA | NA | NA | NA | CHF | CHF | ER001 | Escalate if publication not confirmed by WD+3 EOD | Publication failure or distribution list error | Not Started | 0 | Central FP&A Lead | 2 | No | Awaiting executive sign-off |  |  | NA
Helvetia Advisory AG | Technology | PC000 | PC005 | WD-4 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Pre-Close | Notify business owners | Excel | Notification Log | PC003 | Finish To Start | Medium | 2 | No | NA | No | NA | NA | NA | NA | EUR | CHF | ER001 | Escalate if notifications not confirmed sent by WD-4 12:00 | Notification delivery failure | Complete | 100 | Regional FP&A Lead | 2 | No | Business owner notifications sent - 2 cost centre owners unresponsive, reminders issued |  |  | Generate and send automated notifications to business owners
Helvetia Advisory AG | Technology | PC000 | PC007 | WD-4 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | HR | Regional HR Lead | Regional HR Deputy Lead | Pre-Close | Validate headcount movement | HR System | Headcount Validation Report | PC005 and PC006 | Parallel | High | 4 | Yes | Regional HR Lead | Yes | Detect headcount anomalies vs plan, flag unexpected hires or exits | 80 | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if headcount delta exceeds threshold without explanation | Headcount movement outside approved plan | In Progress | 50 | Regional HR Lead | 3 | No | Headcount validation in progress - Germany restructuring programme created 12 unplanned position changes requiring manual review |  |  | NA
Helvetia Advisory AG | Technology | PC000 | PC008 | WD-4 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Procurement | Regional Procurement Lead | Regional Procurement Deputy Lead | Pre-Close | Open PO review | PO System | PO Commitment Report | PC005 and PC006 | Parallel | Medium | 4 | Yes | Regional Procurement Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if open POs exceed materiality threshold unreviewed | PO aging or commitment spike vs prior period | In Progress | 50 | Regional Procurement Lead | 4 | No | PO review in progress - EUR 340K in aging commitments flagged, procurement lead reviewing |  |  | Flag aging POs over 90 days, identify uncommitted spend at risk
Helvetia Advisory AG | Technology | PC000 | PC009 | WD-4 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Sales Ops | Regional Sales Ops Lead | Regional Sales Ops Deputy Lead | Pre-Close | Revenue pipeline validation | ERP | Pipeline Validation Report | PC005 and PC006 | Parallel | High | 4 | Yes | Regional Sales Ops Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER004 | Create investigation task if pipeline variance unexplained | Revenue pipeline variance vs forecast exceeds 5% | Complete | 100 | Regional Controlling Lead | 3 | No | Revenue pipeline validated - EUR 210K shortfall vs forecast flagged, investigation task created |  |  | Compare pipeline to prior period, flag revenue assumption anomalies
Helvetia Advisory AG | Technology | PC000 | PC010 | WD-3 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Controller | Regional Controlling Lead | Regional Controlling Deputy Lead | Pre-Close | Review expected accruals | ERP | Accrual Estimate List | PC006, PC007, PC008 and PC009 | Finish To Start | High | 6 | Yes | Regional Controlling Lead | Yes | Suggest accruals based on historical patterns, flag missing or anomalous entries | 85 | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER002 | Estimate accrual using historical pattern, escalate to Controller | Expected accrual missing or materially different from prior period | Blocked | 0 | Regional Controlling Lead | 2 | Yes | Blocked pending headcount validation completion |  |  | NA
Helvetia Advisory AG | Technology | PC000 | PC011 | WD-3 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Pre-Close | Review forecast assumptions | Excel | Forecast Assumption Log | PC009 and PC010 | Finish To Start | High | 4 | Yes | Regional FP&A Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if assumptions not reviewed by WD-3 EOD | Forecast assumption change exceeds 5% without commentary | Blocked | 0 | Regional FP&A Lead | 4 | Yes | Blocked pending accrual review |  |  | Variance prediction against prior forecast, flag assumption drift
Helvetia Advisory AG | Technology | CL000 | CL000-1 | WD-1 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Operations | Operations Specialist | Operations Junior Specialist | Close | Reconcile for end of day sales and returns | ERP | Sales Reconciliation Report | Pre-Close Tasks | Finish To Start | High | 4 | No | NA | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if unreconciled balance remains at WD-1 EOD | Unreconciled sales balance above CHF 10K at close | In Progress | 50 | Operations Specialist | 2 | No | Sales reconciliation in progress - EUR 45K unreconciled returns under review |  |  | Monitor sales reconciliation completeness, flag unreconciled items
Helvetia Advisory AG | Technology | CL000 | CL000-2 | WD-1 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Accounts Receivable | Invoicing Specialist | Invoicing Junior Specialist | Close | Complete invoicing | ERP | Invoice Completion Confirmation | Pre-Close Tasks | Finish To Start | High | 3 | No | NA | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if invoicing not complete by WD-1 18:00 | Open invoices remaining after cutoff | In Progress | 50 | Invoicing Specialist | 2 | No | Invoicing in progress - 3 large invoices delayed pending customer purchase order confirmation |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL000-3 | WD-1 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Accounts Receivable | Accounts Receivable Specialist | Accounts Receivable Junior Specialist | Close | Review, reconcile and post for unapplied receipts, deposits, payments, bad debts and chargeback invoices | ERP | AR Reconciliation Report | Pre-Close Tasks | Finish To Start | High | 5 | Yes | Accounts Receivable Specialist | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if unapplied balance exceeds CHF 50K at WD-1 EOD | Unapplied receipts or bad debt spike vs prior period | Blocked | 0 | Regional Controlling Lead | 2 | Yes | AR reconciliation blocked - EUR 178K unapplied receipts unresolved, escalated to Regional Controlling Lead |  |  | Flag unapplied receipts above threshold, suggest posting treatment
Helvetia Advisory AG | Technology | CL000 | CL000-4 | WD-1 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Payroll | Payroll Specialist | Payroll Junior Specialist | Close | Accrue for leaves, benefits, bonus, and time worked not paid till next month | ERP | Payroll Accrual Journal | Pre-Close Tasks | Finish To Start | High | 4 | Yes | Payroll Specialist | Yes | Detect headcount exception in accrual vs validated headcount report | 85 | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER002 | Estimate accrual using historical pattern if submission missing | Payroll accrual variance vs prior period exceeds 5% | In Progress | 50 | Regional HR Lead | 2 | No | Payroll accrual in progress - restructuring-related severance provisions being calculated |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL000-5 | WD-1 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Payroll | Payroll Specialist | Payroll Junior Specialist | Close | Reconcile for employee receivables and tax liabilities | ERP | Payroll Reconciliation Report | Pre-Close Tasks | Finish To Start | Medium | 3 | Yes | Payroll Specialist | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if reconciliation not complete by WD-1 EOD | Unreconciled employee receivable or tax liability | Not Started | 0 | Regional Controlling Lead | 3 | No | Awaiting payroll accrual completion |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL000-6 | WD-1 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Accounts Payable | Accounts Payable Specialist | Accounts Payable Junior Specialist | Close | Identify and update unbooked invoices and post for all payable transactions | ERP | AP Posting Confirmation | Pre-Close Tasks | Finish To Start | High | 4 | Yes | Accounts Payable Specialist | Yes | Flag unbooked invoices above threshold, identify missing accruals | 80 | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER002 | Estimate accrual for late invoices using historical pattern | Unbooked invoice above CHF 25K detected at cutoff | Blocked | 0 | Regional Controlling Lead | 2 | Yes | AP posting blocked - 5 unbooked invoices totalling EUR 187K pending approval, escalated to Regional Controlling Lead |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL000-7 | WD-1 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Treasury | Treasury Specialist | Treasury Junior Specialist | Close | Reconcile bank statements, petty cash, inter-co borrowings/cash transactions, equity/loan accounts and book finance/interest charges | ERP | Treasury Reconciliation Report | Pre-Close Tasks | Finish To Start | High | 5 | Yes | Treasury Specialist | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if bank break exceeds CHF 10K unresolved | Bank reconciliation break or inter-co mismatch | In Progress | 50 | Treasury Specialist | 2 | No | Bank reconciliation in progress - EUR 62K inter-co variance under investigation with BU001 Switzerland |  |  | Flag bank reconciliation breaks, detect unusual inter-co balances
Helvetia Advisory AG | Technology | CL000 | CL001-1 | WD-1 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Verify prior month's reversal entries | ERP | Reversal Verification Log | Pre-Close Tasks | Finish To Start | Medium | 2 | No | NA | No | NA | NA | NA | NA | EUR | CHF | ER001 | Escalate if reversal missing at WD-1 start | Prior month reversal entry absent from journal | Complete | 100 | Regional Snr. Accountant | 1 | No | Prior month reversal entries verified and confirmed |  |  | Verify prior period reversals posted correctly, flag missing reversals
Helvetia Advisory AG | Technology | CL000 | CL001-2 | WD-1 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Contact other departments (AR, AP, Inventory, Payroll) for transaction status | Email/Manual | Department Status Log | Pre-Close Tasks | Finish To Start | Medium | 2 | No | NA | No | NA | NA | NA | NA | EUR | CHF | ER001 | Escalate if no response received within 2 hours | No response from department within SLA | Complete | 100 | Regional Snr. Accountant | 2 | No | Department status chased - AR, AP and Payroll all flagged as in progress with delays expected |  |  | Send automated status requests to AR, AP, Inventory, Payroll teams
Helvetia Advisory AG | Technology | CL000 | CL001-3 | WD-1 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Review and process deferred expenses | ERP | Deferred Expense Journal | Pre-Close Tasks | Finish To Start | Medium | 3 | Yes | Regional Snr. Accountant | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if deferred expense balance materially different from prior period | Deferred expense movement outside expected range | Not Started | 0 | Regional Controlling Lead | 3 | No | Awaiting department transaction status confirmation |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL001-4 | WD-1 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Review prepaid expenses and post journal entries | ERP | Prepaid Expense Journal | Pre-Close Tasks | Finish To Start | Medium | 3 | Yes | Regional Snr. Accountant | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if prepaid balance spike detected | Prepaid expense movement outside expected range | Not Started | 0 | Regional Controlling Lead | 3 | No | Awaiting department transaction status confirmation |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL001-5 | WD-1 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Review accruals and post journal entries | ERP | Accrual Journal Pack | Pre-Close Tasks | Finish To Start | High | 4 | Yes | Regional Snr. Accountant | Yes | Suggest missing accruals based on historical posting patterns | 85 | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER002 | Estimate accrual using prior period if submission missing | Accrual missing or materially below prior period without explanation | Not Started | 0 | Regional Controlling Lead | 2 | No | Awaiting accrual inputs from departments |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL001-6 | WD-1 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Reconcile suspense accounts | ERP | Suspense Account Clearance Report | Pre-Close Tasks | Finish To Start | High | 3 | Yes | Regional Snr. Accountant | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if suspense balance above CHF 5K uncleared at EOD | Suspense account balance remaining at period close | Not Started | 0 | Regional Controlling Lead | 2 | No | Awaiting subledger activity to stabilise |  |  | Flag uncleared suspense balances, suggest clearing entries
Helvetia Advisory AG | Technology | CL000 | CL001-7 | WD-1 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Tax | Regional Tax Lead | Regional Tax Analyst | Close | Calculate and post monthly tax provision entry including current and deferred tax | ERP | Tax Provision Journal | Pre-Close Tasks | Finish To Start | High | 3 | Yes | Regional Tax Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if tax provision not posted by WD-1 EOD | Tax provision materially different from prior period without explanation | Not Started | 0 | Regional Tax Lead | 2 | No | Awaiting payroll and AP posting completion |  |  | Flag tax provision anomalies vs effective tax rate trend
Helvetia Advisory AG | Technology | CL000 | CL001-8 | WD-1 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Run and review monthly depreciation and amortisation journals for all fixed and intangible assets | ERP | Depreciation Journal Confirmation | Pre-Close Tasks | Finish To Start | Medium | 3 | Yes | Regional Snr. Accountant | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if depreciation run not confirmed by WD-1 EOD | Depreciation charge materially different from prior period without explanation | In Progress | 50 | Regional Controlling Lead | 3 | No | Depreciation run initiated - asset register update for restructuring-related disposals pending |  |  | Flag depreciation charge anomalies vs asset register movements
Helvetia Advisory AG | Technology | CL000 | CL001-9 | WD-1 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Treasury | Treasury Specialist | Treasury Junior Specialist | Close | Run monthly FX revaluation for all foreign currency balance sheet positions and book revaluation journals | ERP | FX Revaluation Journal | CL000-3, CL000-6 and CL000-7 | Finish To Start | High | 3 | Yes | Treasury Specialist | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if FX revaluation not posted by WD-1 EOD | FX revaluation gain or loss materially different from prior period without explanation | Blocked | 0 | Treasury Specialist | 2 | Yes | Blocked - FX revaluation cannot run until AR and AP postings complete |  |  | FX anomaly checks vs market rates, flag unusual revaluation movements
Helvetia Advisory AG | Technology | CL000 | CL002 | WD-1 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Review and reconcile clearing accounts | ERP | Clearing Account Report | CL001 | Finish To Start | High | 3 | Yes | Regional Snr. Accountant | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if clearing account aged items exceed CHF 10K | Clearing account item aged over 30 days | Not Started | 0 | Regional Controlling Lead | 2 | No | Awaiting CL001 series completion |  |  | Check clearing account completeness, flag aged items
Helvetia Advisory AG | Technology | CL000 | CL003-1 | WD-1 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Reconcile and close subledger | ERP | Subledger Close Confirmation | CL002 | Finish To Start | High | 4 | Yes | Regional Controlling Lead | Yes | Missing account checks - validate all accounts posted vs expected | 90 | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate immediately if subledger close fails | Any account in expected posting list with zero balance | Not Started | 0 | Regional Controlling Lead | 1 | No | Awaiting clearing account reconciliation |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL003-2 | WD-1 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | Controller | Regional Controlling Lead | Regional Controlling Deputy Lead | Close | Reconcile intercompany balances and confirm matched pairs with counterpart entities before period lock | ERP | Intercompany Reconciliation Confirmation | CL002 | Finish To Start | High | 4 | Yes | Regional Controlling Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if intercompany reconciliation not confirmed by WD-1 EOD | Intercompany mismatch above CHF 10K unresolved at period lock | Not Started | 0 | Regional Controlling Lead | 2 | No | Awaiting subledger close - inter-co mismatch with BU001 Switzerland still unresolved |  |  | Detect intercompany mismatch patterns, suggest offset entries
Helvetia Advisory AG | Technology | CL000 | CL004 | WD+0 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Close | Generate P&L | ERP | P&L Report | CL003-1 and CL003-2 | Finish To Start | High | 2 | Yes | Regional FP&A Lead | Yes | Missing account checks on P&L, flag zero-balance accounts expected to post | 90 | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER004 | Create investigation task for unexplained P&L movement | P&L line materially different from prior period without explanation | Not Started | 0 | Regional FP&A Lead | 1 | No | Awaiting subledger and intercompany close |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL005 | WD+0 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Close | Generate flash reports | ERP | Flash Report Pack | CL003-1, CL003-2 and CL004 | Parallel | High | 2 | Yes | Regional FP&A Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if flash report not generated by WD+0 12:00 | Flash report generation failure or missing data feed | Not Started | 0 | Regional FP&A Lead | 2 | No | Awaiting P&L generation |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL006 | WD+0 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Close | Generate forecast update | ERP | Updated Forecast File | CL003-1, CL003-2 and CL004 | Parallel | High | 3 | Yes | Regional FP&A Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if forecast update not complete by WD+0 EOD | Forecast file missing or not refreshed with actuals | Not Started | 0 | Regional FP&A Lead | 2 | No | Awaiting P&L generation |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL007 | WD+0 | 2026 P05 | Monthly | BU | BU002 | EMEA | DACH | Germany | BU002 | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Close | Draft commentary | Excel | Draft Commentary Document | CL003-1, CL003-2 and CL004 | Parallel | High | 4 | Yes | Regional FP&A Lead | Yes | CFO status email draft based on current close progress | 75 | NA | NA | EUR | CHF | ER001 | Escalate if commentary not drafted by WD+0 EOD | Commentary missing or inconsistent with P&L output | Not Started | 0 | Regional FP&A Lead | 4 | No | Awaiting P&L generation - commentary cannot begin without final numbers |  |  | NA
Helvetia Advisory AG | Technology | PC000 | PC005 | WD-4 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Pre-Close | Notify business owners | Excel | Notification Log | PC003 | Finish To Start | Medium | 2 | No | NA | No | NA | NA | NA | NA | EUR | CHF | ER001 | Escalate if notifications not confirmed sent by WD-4 12:00 | Notification delivery failure | Complete | 100 | Regional FP&A Lead | 2 | No | Business owner notifications sent and confirmed - all owners acknowledged within 1 hour |  |  | Generate and send automated notifications to business owners
Helvetia Advisory AG | Technology | PC000 | PC007 | WD-4 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | HR | Regional HR Lead | Regional HR Deputy Lead | Pre-Close | Validate headcount movement | HR System | Headcount Validation Report | PC005 and PC006 | Parallel | High | 4 | Yes | Regional HR Lead | Yes | Detect headcount anomalies vs plan, flag unexpected hires or exits | 80 | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if headcount delta exceeds threshold without explanation | Headcount movement outside approved plan | Complete | 100 | Regional HR Lead | 3 | No | Headcount validated - no exceptions, Austria headcount stable vs plan |  |  | NA
Helvetia Advisory AG | Technology | PC000 | PC008 | WD-4 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Procurement | Regional Procurement Lead | Regional Procurement Deputy Lead | Pre-Close | Open PO review | PO System | PO Commitment Report | PC005 and PC006 | Parallel | Medium | 4 | Yes | Regional Procurement Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if open POs exceed materiality threshold unreviewed | PO aging or commitment spike vs prior period | Complete | 100 | Regional Procurement Lead | 4 | No | PO review complete - no aging commitments above threshold |  |  | Flag aging POs over 90 days, identify uncommitted spend at risk
Helvetia Advisory AG | Technology | PC000 | PC009 | WD-4 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Sales Ops | Regional Sales Ops Lead | Regional Sales Ops Deputy Lead | Pre-Close | Revenue pipeline validation | ERP | Pipeline Validation Report | PC005 and PC006 | Parallel | High | 4 | Yes | Regional Sales Ops Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER004 | Create investigation task if pipeline variance unexplained | Revenue pipeline variance vs forecast exceeds 5% | Complete | 100 | Regional Controlling Lead | 3 | No | Revenue pipeline validated - 2% above forecast, within threshold, no investigation required |  |  | Compare pipeline to prior period, flag revenue assumption anomalies
Helvetia Advisory AG | Technology | PC000 | PC010 | WD-3 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Controller | Regional Controlling Lead | Regional Controlling Deputy Lead | Pre-Close | Review expected accruals | ERP | Accrual Estimate List | PC006, PC007, PC008 and PC009 | Finish To Start | High | 6 | Yes | Regional Controlling Lead | Yes | Suggest accruals based on historical patterns, flag missing or anomalous entries | 85 | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER002 | Estimate accrual using historical pattern, escalate to Controller | Expected accrual missing or materially different from prior period | Complete | 100 | Regional Controlling Lead | 2 | No | Expected accruals reviewed and pre-approved - Austria accrual list clean and consistent with prior period |  |  | NA
Helvetia Advisory AG | Technology | PC000 | PC011 | WD-3 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Pre-Close | Review forecast assumptions | Excel | Forecast Assumption Log | PC009 and PC010 | Finish To Start | High | 4 | Yes | Regional FP&A Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if assumptions not reviewed by WD-3 EOD | Forecast assumption change exceeds 5% without commentary | Complete | 100 | Regional FP&A Lead | 4 | No | Forecast assumptions signed off ahead of schedule |  |  | Variance prediction against prior forecast, flag assumption drift
Helvetia Advisory AG | Technology | CL000 | CL000-1 | WD-1 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Operations | Operations Specialist | Operations Junior Specialist | Close | Reconcile for end of day sales and returns | ERP | Sales Reconciliation Report | Pre-Close Tasks | Finish To Start | High | 4 | No | NA | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if unreconciled balance remains at WD-1 EOD | Unreconciled sales balance above CHF 10K at close | Complete | 100 | Operations Specialist | 2 | No | Sales and returns reconciled with zero unreconciled balance |  |  | Monitor sales reconciliation completeness, flag unreconciled items
Helvetia Advisory AG | Technology | CL000 | CL000-2 | WD-1 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Accounts Receivable | Invoicing Specialist | Invoicing Junior Specialist | Close | Complete invoicing | ERP | Invoice Completion Confirmation | Pre-Close Tasks | Finish To Start | High | 3 | No | NA | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if invoicing not complete by WD-1 18:00 | Open invoices remaining after cutoff | Complete | 100 | Invoicing Specialist | 2 | No | All invoicing completed 2 hours ahead of cutoff |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL000-3 | WD-1 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Accounts Receivable | Accounts Receivable Specialist | Accounts Receivable Junior Specialist | Close | Review, reconcile and post for unapplied receipts, deposits, payments, bad debts and chargeback invoices | ERP | AR Reconciliation Report | Pre-Close Tasks | Finish To Start | High | 5 | Yes | Accounts Receivable Specialist | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if unapplied balance exceeds CHF 50K at WD-1 EOD | Unapplied receipts or bad debt spike vs prior period | Complete | 100 | Regional Controlling Lead | 2 | No | AR fully reconciled - no unapplied receipts, clean period |  |  | Flag unapplied receipts above threshold, suggest posting treatment
Helvetia Advisory AG | Technology | CL000 | CL000-4 | WD-1 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Payroll | Payroll Specialist | Payroll Junior Specialist | Close | Accrue for leaves, benefits, bonus, and time worked not paid till next month | ERP | Payroll Accrual Journal | Pre-Close Tasks | Finish To Start | High | 4 | Yes | Payroll Specialist | Yes | Detect headcount exception in accrual vs validated headcount report | 85 | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER002 | Estimate accrual using historical pattern if submission missing | Payroll accrual variance vs prior period exceeds 5% | Complete | 100 | Regional HR Lead | 2 | No | Payroll accruals posted - no exceptions, headcount stable |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL000-5 | WD-1 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Payroll | Payroll Specialist | Payroll Junior Specialist | Close | Reconcile for employee receivables and tax liabilities | ERP | Payroll Reconciliation Report | Pre-Close Tasks | Finish To Start | Medium | 3 | Yes | Payroll Specialist | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if reconciliation not complete by WD-1 EOD | Unreconciled employee receivable or tax liability | Complete | 100 | Regional Controlling Lead | 3 | No | Employee receivables and tax liabilities reconciled with no breaks |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL000-6 | WD-1 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Accounts Payable | Accounts Payable Specialist | Accounts Payable Junior Specialist | Close | Identify and update unbooked invoices and post for all payable transactions | ERP | AP Posting Confirmation | Pre-Close Tasks | Finish To Start | High | 4 | Yes | Accounts Payable Specialist | Yes | Flag unbooked invoices above threshold, identify missing accruals | 80 | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER002 | Estimate accrual for late invoices using historical pattern | Unbooked invoice above CHF 25K detected at cutoff | Complete | 100 | Regional Controlling Lead | 2 | No | All AP transactions posted - no unbooked invoices above threshold |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL000-7 | WD-1 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Treasury | Treasury Specialist | Treasury Junior Specialist | Close | Reconcile bank statements, petty cash, inter-co borrowings/cash transactions, equity/loan accounts and book finance/interest charges | ERP | Treasury Reconciliation Report | Pre-Close Tasks | Finish To Start | High | 5 | Yes | Treasury Specialist | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if bank break exceeds CHF 10K unresolved | Bank reconciliation break or inter-co mismatch | Complete | 100 | Treasury Specialist | 2 | No | Bank and inter-co reconciliation complete - all inter-co balances matched with counterpart entities |  |  | Flag bank reconciliation breaks, detect unusual inter-co balances
Helvetia Advisory AG | Technology | CL000 | CL001-1 | WD-1 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Verify prior month's reversal entries | ERP | Reversal Verification Log | Pre-Close Tasks | Finish To Start | Medium | 2 | No | NA | No | NA | NA | NA | NA | EUR | CHF | ER001 | Escalate if reversal missing at WD-1 start | Prior month reversal entry absent from journal | Complete | 100 | Regional Snr. Accountant | 1 | No | Prior month reversals confirmed - all posted correctly |  |  | Verify prior period reversals posted correctly, flag missing reversals
Helvetia Advisory AG | Technology | CL000 | CL001-2 | WD-1 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Contact other departments (AR, AP, Inventory, Payroll) for transaction status | Email/Manual | Department Status Log | Pre-Close Tasks | Finish To Start | Medium | 2 | No | NA | No | NA | NA | NA | NA | EUR | CHF | ER001 | Escalate if no response received within 2 hours | No response from department within SLA | Complete | 100 | Regional Snr. Accountant | 2 | No | All departments confirmed transaction status - no delays reported |  |  | Send automated status requests to AR, AP, Inventory, Payroll teams
Helvetia Advisory AG | Technology | CL000 | CL001-3 | WD-1 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Review and process deferred expenses | ERP | Deferred Expense Journal | Pre-Close Tasks | Finish To Start | Medium | 3 | Yes | Regional Snr. Accountant | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if deferred expense balance materially different from prior period | Deferred expense movement outside expected range | Complete | 100 | Regional Controlling Lead | 3 | No | Deferred expenses reviewed and journals posted ahead of schedule |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL001-4 | WD-1 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Review prepaid expenses and post journal entries | ERP | Prepaid Expense Journal | Pre-Close Tasks | Finish To Start | Medium | 3 | Yes | Regional Snr. Accountant | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if prepaid balance spike detected | Prepaid expense movement outside expected range | Complete | 100 | Regional Controlling Lead | 3 | No | Prepaid expenses reviewed and posted - no material movements |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL001-5 | WD-1 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Review accruals and post journal entries | ERP | Accrual Journal Pack | Pre-Close Tasks | Finish To Start | High | 4 | Yes | Regional Snr. Accountant | Yes | Suggest missing accruals based on historical posting patterns | 85 | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER002 | Estimate accrual using prior period if submission missing | Accrual missing or materially below prior period without explanation | Complete | 100 | Regional Controlling Lead | 2 | No | Accruals complete - no missing items flagged by AI suggested accruals feature |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL001-6 | WD-1 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Reconcile suspense accounts | ERP | Suspense Account Clearance Report | Pre-Close Tasks | Finish To Start | High | 3 | Yes | Regional Snr. Accountant | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if suspense balance above CHF 5K uncleared at EOD | Suspense account balance remaining at period close | Complete | 100 | Regional Controlling Lead | 2 | No | Suspense accounts fully cleared - zero balance at close |  |  | Flag uncleared suspense balances, suggest clearing entries
Helvetia Advisory AG | Technology | CL000 | CL001-7 | WD-1 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Tax | Regional Tax Lead | Regional Tax Analyst | Close | Calculate and post monthly tax provision entry including current and deferred tax | ERP | Tax Provision Journal | Pre-Close Tasks | Finish To Start | High | 3 | Yes | Regional Tax Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if tax provision not posted by WD-1 EOD | Tax provision materially different from prior period without explanation | Complete | 100 | Regional Tax Lead | 2 | No | Tax provision posted - current tax EUR 89K, consistent with prior period effective rate |  |  | Flag tax provision anomalies vs effective tax rate trend
Helvetia Advisory AG | Technology | CL000 | CL001-8 | WD-1 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Run and review monthly depreciation and amortisation journals for all fixed and intangible assets | ERP | Depreciation Journal Confirmation | Pre-Close Tasks | Finish To Start | Medium | 3 | Yes | Regional Snr. Accountant | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if depreciation run not confirmed by WD-1 EOD | Depreciation charge materially different from prior period without explanation | Complete | 100 | Regional Controlling Lead | 3 | No | Depreciation run complete - EUR 31K charge in line with asset register |  |  | Flag depreciation charge anomalies vs asset register movements
Helvetia Advisory AG | Technology | CL000 | CL001-9 | WD-1 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Treasury | Treasury Specialist | Treasury Junior Specialist | Close | Run monthly FX revaluation for all foreign currency balance sheet positions and book revaluation journals | ERP | FX Revaluation Journal | CL000-3, CL000-6 and CL000-7 | Finish To Start | High | 3 | Yes | Treasury Specialist | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if FX revaluation not posted by WD-1 EOD | FX revaluation gain or loss materially different from prior period without explanation | Complete | 100 | Treasury Specialist | 2 | No | FX revaluation posted - EUR 6K net gain, minimal movement |  |  | FX anomaly checks vs market rates, flag unusual revaluation movements
Helvetia Advisory AG | Technology | CL000 | CL002 | WD-1 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Review and reconcile clearing accounts | ERP | Clearing Account Report | CL001 | Finish To Start | High | 3 | Yes | Regional Snr. Accountant | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if clearing account aged items exceed CHF 10K | Clearing account item aged over 30 days | Complete | 100 | Regional Controlling Lead | 2 | No | Clearing accounts fully reconciled - no aged items |  |  | Check clearing account completeness, flag aged items
Helvetia Advisory AG | Technology | CL000 | CL003-1 | WD-1 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Accounting | Regional Snr. Accountant | Regional Accountant | Close | Reconcile and close subledger | ERP | Subledger Close Confirmation | CL002 | Finish To Start | High | 4 | Yes | Regional Controlling Lead | Yes | Missing account checks - validate all accounts posted vs expected | 90 | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate immediately if subledger close fails | Any account in expected posting list with zero balance | Complete | 100 | Regional Controlling Lead | 1 | No | Subledger closed cleanly - no zero balance exceptions identified |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL003-2 | WD-1 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | Controller | Regional Controlling Lead | Regional Controlling Deputy Lead | Close | Reconcile intercompany balances and confirm matched pairs with counterpart entities before period lock | ERP | Intercompany Reconciliation Confirmation | CL002 | Finish To Start | High | 4 | Yes | Regional Controlling Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if intercompany reconciliation not confirmed by WD-1 EOD | Intercompany mismatch above CHF 10K unresolved at period lock | Complete | 100 | Regional Controlling Lead | 2 | No | Intercompany balances confirmed with all counterparts including BU001 and BU002 |  |  | Detect intercompany mismatch patterns, suggest offset entries
Helvetia Advisory AG | Technology | CL000 | CL004 | WD+0 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Close | Generate P&L | ERP | P&L Report | CL003-1 and CL003-2 | Finish To Start | High | 2 | Yes | Regional FP&A Lead | Yes | Missing account checks on P&L, flag zero-balance accounts expected to post | 90 | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER004 | Create investigation task for unexplained P&L movement | P&L line materially different from prior period without explanation | Complete | 100 | Regional FP&A Lead | 1 | No | P&L generated - revenue EUR 1.8M, 2% above forecast, clean close |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL005 | WD+0 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Close | Generate flash reports | ERP | Flash Report Pack | CL003-1, CL003-2 and CL004 | Parallel | High | 2 | Yes | Regional FP&A Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if flash report not generated by WD+0 12:00 | Flash report generation failure or missing data feed | Complete | 100 | Regional FP&A Lead | 2 | No | Flash reports generated and distributed - Austria fastest submission this period |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL006 | WD+0 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Close | Generate forecast update | ERP | Updated Forecast File | CL003-1, CL003-2 and CL004 | Parallel | High | 3 | Yes | Regional FP&A Lead | No | NA | NA | VR001 | BU variance >5% or >CHF 100K triggers review | EUR | CHF | ER001 | Escalate if forecast update not complete by WD+0 EOD | Forecast file missing or not refreshed with actuals | Complete | 100 | Regional FP&A Lead | 2 | No | Forecast update complete - actuals loaded and reviewed |  |  | NA
Helvetia Advisory AG | Technology | CL000 | CL007 | WD+0 | 2026 P05 | Monthly | BU | BU003 | EMEA | DACH | Austria | BU003 | FP&A | Regional FP&A Lead | Regional FP&A Analyst | Close | Draft commentary | Excel | Draft Commentary Document | CL003-1, CL003-2 and CL004 | Parallel | High | 4 | Yes | Regional FP&A Lead | Yes | CFO status email draft based on current close progress | 75 | NA | NA | EUR | CHF | ER001 | Escalate if commentary not drafted by WD+0 EOD | Commentary missing or inconsistent with P&L output | Complete | 100 | Regional FP&A Lead | 4 | No | Commentary drafted and ready for submission - no consistency issues flagged |  |  | NA

## Index
Data Field | Definition
Organization Name | Legal or trading name of the organization running the close process
Industry | Sector the organization operates in, used to contextualize benchmarks and thresholds
Parent Task ID | ID of the parent task group this task belongs to, used for hierarchical rollup and progress tracking
Task ID | Unique identifier for each individual task, used for dependency mapping and audit trail
Working Day | Relative working day in the close calendar when the task is due, expressed as WD
Fiscal Period | The accounting period this close cycle belongs to, expressed as year and period number
Period Type | Frequency of the close cycle this task belongs to - Monthly, Quarterly, or Annual
Organization Level | Hierarchical level at which this task is performed - BU, Region, Area, or Global
Lowest Org Level Name | Specific name of the organizational unit performing the task at the level defined in Organization Level
Area | Geographic or operational area the task belongs to - used for consolidation grouping
Region | Sub-area geographic or operational region the task belongs to
Country | Sub-area geographic or operational country the task belongs to
Entity | Legal entity or business unit code the task is associated with - NA if task is above entity level
Owner Function | Department or functional team responsible for completing the task
Task Owner | Named role of the primary individual accountable for task completion
Backup Task Owner | Named role of the secondary individual who assumes ownership if the primary owner is unavailable
Phase | Stage of the close cycle the task belongs to - Pre-Close, Close, Close-to-Post-Close, or Post-Close
Task Description | Plain English description of what the task involves and what needs to be completed
Input Source | System, tool, or document that provides the data or information needed to complete the task
Output Artifact | Document, report, or confirmation produced when the task is completed successfully
Dependency Task | Task ID or task group that must be completed before this task can begin
Dependency Type | Nature of the dependency relationship - Finish To Start means predecessor must fully complete first; Parallel means tasks can run simultaneously
Priority | Criticality of the task to the close timeline - High, Medium, or Low
SLA Hours | Time within which task is to be completed
Human Approval Required | Indicates whether a human sign-off is required before the task can be marked complete — Yes or No
Approval Role | Named role of the individual who must approve the task output if Human Approval Required is Yes
AI Enabled | Indicates whether an AI action is configured for this task - Yes or No
AI Action | Description of what the AI specifically does for this task when AI Enabled is Yes
AI Confidence Threshold | Minimum AI confidence score on a scale of 0 to 100 required before AI output is accepted without mandatory human review - higher thresholds apply to tasks with greater financial risk
Variance Threshold Rule ID | Reference ID linking to the Variance Rules sheet - applicable to financial tasks only, NA for non-financial tasks
Variance Threshold Rule | Plain English description of the variance threshold that triggers AI review or escalation for this task
Functional Currency | Currency in which the business is operational
Reporting Currency | Currency in which the financial results are reported
Escalation Rule ID | Reference ID linking to the corresponding rule in the Exception Rules sheet
Escalation Rule | Plain English description of the condition and action that triggers escalation for this task
Exception Logic | Specific condition or event that constitutes an exception for this task and triggers the escalation rule
Status | Current completion state of the task - default value is Not Started; updates to In Progress, Complete, or Blocked during the close cycle
Completion % | Percentage of the task completed - default value is 0%, updated manually or by system during execution
Escalation Role | Named role of the individual or team notified when an escalation is triggered for this task
Escalation After Hours | Number of hours after an SLA breach before the escalation notification is automatically fired
Escalated | Indicates whether a task was escalated when SLA was breached - Yes when escalated, and No - when escalation is not applicable for current task status
Comments | Free text field for notes, clarifications, or observations added during task execution - blank by default
Audit Timestamp | System-generated date and time recorded when a status change or approval action occurs on the task
Audit Stamp | System-generated identifier recording which user or system process triggered the last status change or approval action
AI Action - Planned Wave 2 | Lists potential AI actions that can be tested and deployed as part of wave 2

## Variance Rules
Rule No. | Level | Percent | Absolute CHF
VR001 | BU | 5% | 100000
VR002 | Region | 4% | 500000
VR003 | Area | 3% | 1000000
VR004 | Global | 3% | 1500000
IF variance exceeds threshold
THEN
Generate root cause analysis Generate commentary draft Assign task Notify owner Escalate after SLA breach
The threshold rules are based on Reporting Currency

## Exception Rules
Rule No. | Condition | AI action | Escalation
ER001 | Missing submission | Reminder after one hour | Escalate after two reminders
ER002 | Late accrual | Estimate using historical pattern | Controller review
ER003 | Data refresh failed | Retry process | IT escalation
ER004 | Large unexplained variance | Create investigation task | Finance lead
ER005 | Hierarchy mismatch | Suggest mapping fix | Master data owner
ER006 | Prior period restatement | Impact analysis | Global Controller

## Approval Workflow
Levels | Approval Decision
Level 1 | AI Confidence Score
0 to100
Level 2 | Human decision:
Approve
Approve with notes
Return for revision
Escalate
Level 3 | AI recommendation:
Low risk
Moderate risk
Critical
Level 4 | Audit capture:
Reason
Timestamp
Variance impact
WD-/+x | AI
WD-5 | AI: Generate dynamic close schedule Identify entities with historic delays Predict bottlenecks Human sign off: FP&A Director
WD-4 | AI: Predict missing submissions Identify abnormal volume assumptions

## AI Features
AI features for Wave 1:
1 | CFO status email draft
2 | Suggested accruals
3 | Variance root cause suggestions
4 | Missing account checks
5 | Narrative consistency check
6 | Headcount exception detection